**PROGRESS CLAUSE:** Submit a Progress / Critical Path Method (CPM) Schedule. The Engineer for this project is as follows:

Engineer Name, P.E.

Owner/Agency

Mailing Address

City, State Zip Code

Office Phone Number

Email Address

After receiving Notice of Award, start work on the date approved by the Engineer, which date must be no earlier than **Month, Day, Year**. In no case, may any work be commenced prior to receipt of formal notice of award by the Department.

***This section is for work day or calendar day projects and must be deleted for other projects.***

The entire project must be completed in **XX** work days / calendar days. Work / Calendar days will be charged on the date work starts, or on the date designated as the starting date in the Progress Schedule whichever occurs earlier.

***This section is for calendar date projects and must be deleted for other projects.***

All contract work for **Stage X** must be complete and the road/bridge fully open to traffic no later than the interim completion date of **Month, Day, Year**.

All contract work for **Stage X** must be complete and the road/bridge fully open to traffic no later than the interim completion date of **Month, Day, Year**.

All contract work, except for **XXXX**, must be complete on or before the interim completion date of **Month, Day, Year**.

The project must be completely open to traffic on or before the interim completion date of **Month, Day, Year**.

The entire project must be completed on or before the final completion date of **Month, Day, Year**.

The final completion date for this project is **Month, Day, Year** this date is to accommodate an establishment period for turf establishment. All contract work except turf establishment must be completed in its entirety, by the interim completion date of **Month, Day, Year**. Turf establishment must be placed by the interim completion date of **Month, Day, Year**. The contractor has until the interim completion date of **Month, Day, Year** to meet the specifications associated with turf establishment.

***This section is for expedited projects and must be deleted for other projects.***

This project is on an expedited schedule based on a 6 day or 7 day work week. The Contractor is expected to mobilize sufficient labor resources and equipment and to work the required overtime to maintain the expedited schedule.

Failure by the Contractor to meet interim or final completion dates will result in the assessment of liquidated damages in accordance with subsections 108.10.C.1 and 108.10.C.2 of the Standard Specifications for Construction and the Special Provision for Liquidated Damages for Other Department Costs for Job Number XXXXXX. Liquidated damages will be assessed separately and simultaneously for failure to meet interim and final completion dates. Liquidated damages will continue to be assessed for each calendar day that the work associated with the interim or final completion dates remains incomplete, even if these days extend into or beyond seasonal suspension, unless approved otherwise by the Engineer.

Unless specific pay items are provided in the contract any extra costs incurred by the Contractor due to cold-weather protection and winter grading will not be paid for separately, but will be included in payment of other contract items.

After award and prior to the start of work, the Contractor must attend a preconstruction meeting with the Engineer. The Engineer will determine the day, time and place for the preconstruction meeting. The meeting will be conducted after project award and may be rescheduled if there are delays in the award of the project.

The named subcontractor(s) for, Designated and/or Specialty Items, as shown in the proposal, is recommended to be at the preconstruction meeting if such items materially affect the work schedule.

***General topics that will affect scheduling can placed here including the reference to the specific contract document.***

Lane rentals assessments will be applied per the Special Provision for \_\_\_\_\_\_\_\_\_\_.

The Contractor must comply with all local ordinances (noise, etc.) as described in the Special Provision for \_\_\_\_\_\_\_\_\_\_.

The Contractor may be required to meet with Department representatives for a post-construction review meeting, as directed by the Engineer. The Engineer will schedule the meeting.

Failure on the part of the Contractor to carry out the provisions of this Progress Clause may be considered sufficient cause to prevent bidding future projects.