## Sheet1
100 | ADMINISTRATION
100 | Award Letter |  | Award YYYY-MM-DD
101 | Contract Form
| Progress Schedule | 1130 | 1130 YYYY-MM-DD
| Weekly Statement of Work Days Charged | 1116 | 1116 001
| Critical Path Method(CPM) |  | CPM YYYY-MM-DD
Workzone Enforcement Contracts
102 | Sub-Contracts
| All SubContracts | 1302A | 1302A ABC Contracting
| Commercially Useful Function (CUF) Project Site Review | 4109 | 4109 YYYY-MM-DD ABC Contracting
| DBE Participation (blue sheets) | 178 | 178
| DBE Trucker Project Site Review | 1992 | 1992
103 | Work Orders
| Notice of Non-Compliance with Contract | 1165 | 1165 YYYY-MM-DD
| Work Orders | 1137 | 1137 001 Drainage Changes
104 | Contract Modifications
| Value Engineering Change Proposal | 1962 | 1962 YYYY-MM-DD Structural Steel ABC Contracting
| Contract Modification |  | CM 001
FHWA 1365 Pre-Approvals
| FHWA 1365 Pre-Approvals | 1365 | 1365 YYYY-MM-DD Structural Steel
Extension of Time
| Extension of Time | 1100A | 1100A 001
Supporting Documents
105 | Contractor Claims and Force Account
| Force Account Statement | 1101 | 1101 YYYY-MM-DD GJM Rut Filling ABC Contracting
| Force Account Daily Field Record | 1101A
Damage Claim Notices
| Damage Claims Notices | 1119D | 1119D 001 Smith John
106 | Estimates and Closeout Package
| Construction Pay Estimate Report(Bi-Weekly Pay Estimates) |  | Pay Estimate 001
| Construction Pay Estimate Report(Final Pay Estimate) |  | Pay Estimate 001 Final
| Stockpile Data |  | Stock Pile YYYY-MM-DD Steel
Closeout Documents
| Final Acceptance/Certification Report | 1120 | 1120
| Final Estimate Package Memo | 1105 | 1105
| Final Estimate Review Summary | 1147 | 1147 or 1147C
| Post Certification of Subcontract compliance (Copy) | 1386 | 1386
| Final 2124A | 2124A | 2124A
| Final project voucher summary(Signed from CSD) |  | Final project voucher summary
| Work Completion letter from contractor |  | Completion Letter YYYY-MM-DD
107 | Warranty Documentation
| Warranty Correspondence |  | Corr YYYY-MM-DD GJM Warranty
| Bridge | 1802 | 1802 YYYY-MM-DD
| HMA | Series 1134 | 1134 YYYY-MM-DD
108 | Correspondence
| Email |  | Corr YYYY-MM-DD GJM Lane Closures
| General Correspondence |  | Corr YYYY-MM-DD GJM Lane Closures
109 | Preconstruction and Progress Meetings
| Damage Claim Program |  | Damage Claim Program
| Safety Program |  | Safety Program
| Subcontractor's List |  | Subcontractor's List
| Emergency Contact List |  | Emergency Contact List
| Meeting Minutes |  | Meeting Minutes YYYY-MM-DD
| WorkZone Access Plan |  | WorkZone Access Plan
110 | Utilities, Permits and Real Estate
| Property Agreements and release |  | Property Agreements & Release Smith John
| Construction Permit |  | Construction Permit
| Miss Dig Document request |  | Miss Dig YYYY-MM-DD ABC Contracting
200 | FIELD RECORDS
200 | Inspector's Daily Reports
| IDR |  | IDR YYYY-MM-DD GJM
| IDR with Rev and Seq |  | IDR YYYY-MM-DD GJM R1 S1
200-1 | Photographs & Videos
| Photo |  | Photo YYYY-MM-DD GJM Station 24+65 Broken Casting
201 | Shop Drawing and submittals
| Approved | SD | SD 001 YYYY-MM-DD Structure Steel Retrofit
| Shop Drawing | SD | SD 001 YYYY-MM-DD Structure Steel Retrofit Approved
| Original Comments | SD | SD 001 YYYY-MM-DD Structure Steel Retrofit
| Rejected | SD | SD 001 YYYY-MM-DD Structure Steel Retrofit Rejected
| Review in Progress | SD | SD 001 YYYY-MM-DD Structure Steel Retrofit Pending
201-1 | Request For Information(RFI) |  | RFI YYYY-MM-DD
201-2 | Survey
| Contractor Staking Quality Control Plan |  | CSQCP YYYY-MM-DD
| As-constructed Earth Work Calcs | Calc | Calc YYYY-MM-DD GJM (Name of item of work)
| Cross-Sections | Calc | Calc YYYY-MM-DD GJM (Name of item of work)
202 | Earthwork
| Grade Check | 1145 | 1145 YYYY-MM-DD GJM Clay Grade
| Record Of Soils Recommendations | 583 | 0583 YYYY-MM-DD NB Sta 24+65 to 65+24
| Delivery Tickets |  | placed in paper file
| Volume Sheets | 1198 | 1198 YYYY-MM-DD GJM Sta 24+65 to 65+24
| Earth Work Data Sheet | 1124 | 1124 YYYY-MM-DD GJM Sta 24+65 to 65+24
202-1 | NPDES and SESC Reports
| NPDES | 1126 | 1126 001 YYYY-MM-DD GJM
| Environmental Permits |  | Permit
| Notice of Termination(NOT) |  | NOT
| Notice of Completion(NOC) |  | NOC
203 | Bases
| Subbase |  | Subbase YYYY-MM-DD GJM
| Aggregates |  | Agg Base YYYY-MM-DD GJM
| Rubbilizing Portland Cement Concrete Pavement |  | Rubblilize pavt YYYY-MM-DD GJM
| Geotextile for Base |  | Geotextile YYYY-MM-DD GJM
| HMA Base Crushing and Shaping |  | Crush & Shape YYYY-MM-DD GJM
| Aggregate Delivery Tickets |  | placed in paper file
| Subbase calculations | Calc | Calc YYYY-MM-DD GJM Agg Base
| Sketches and calculations | Calc | Calc YYYY-MM-DD GJM (Name of item of work)
| Grade Check | 1145 | 1145 YYYY-MM-DD GJM Agg Base Sta 24+65 to 65+24
204 | Drainage
| Pumpstations |  | Pumpstation YYYY-MM-DD GJM
| Drainage Items |  | (Name of item of work) YYYY-MM-DD GJM
| Sewers |  | (Name of item of work) YYYY-MM-DD GJM
| CPE and CPV Pipe Inst and Mandrel Testing Results sewers | 1974 | 1974 YYYY-MM-DD
| CPE and CPV Pipe Inst and Mandrel Testing Results culvert | 1975 | 1975 YYYY-MM-DD
| Underdrains |  | (Name of item of work) YYYY-MM-DD GJM
| Culverts |  | (Name of item of work) YYYY-MM-DD GJM
205 | Hot Mix Asphalt (HMA)
| HMA Crack Treatment |  | HMA Crack Treatment YYYY-MM-DD GJM Sta 24+65 to 65+24
| Surface Seal |  | Surface Seal YYYY-MM-DD GJM Sta 24+65 to 65+24
| Micro-surfacing |  | Micro Surfacing YYYY-MM-DD GJM Sta 24+65 to 65+24
| Chip Seals |  | Chip Seal YYYY-MM-DD GJM Sta 24+65 to 65+24
| Slurry Seal |  | Slurry Seal YYYY-MM-DD GJM Sta 24+65 to 65+24
| HMA Delivery Tickets |  | placed in paper file
| Sketches and calculations | Calc | Calc YYYY-MM-DD GJM HMA pavement
| Ride Quality |  | Ride Quality YYYY-MM-DD US131 NB Sta 24+65 to 65+24
206 | Concrete
| Inspector’s Report of Concrete placed - Roadway | 1174R | 1174R 001
| Inspector’s Report of Concrete placed - Structure | 1174S | 1174S 001
| Coring Request | 500 | 500 YYYY-MM-DD Sta 24+65 123145
| Contractor's QC Test Reports (Air, slump, temp) |  | Conc QC YYYY-MM-DD ABC Contracting
| Ride Quality |  | Ride Quality YYYY-MM-DD US131 NB Sta 24+65 to 65+24
| Concrete Delivery Tickets |  | placed in paper file
| Sketches and calculations | Calc | Calc YYYY-MM-DD GJM Misc Concrete
207 | Structure
| Bridge Decks Concrete Depth Measurements | 1131 | 1131 YYYY-MM-DD GJM B01 Wet
| Bridge Reinforcing Computations | 1138 | 1138 YYYY-MM-DD GJM S02
| Foundation Piling Record (LRFD) | 1161(L) | 1161 YYYY-MM-DD GJM S02 Abut A
| Pile Driving Table | 1157A | 1157A YYYY-MM-DD GJM S02 Abut A
| Structure - Clearance Measurements | 1190 | 1190 YYYY-MM-DD GJM US131 S02
| Structure Painting forms | 1941 | 1941 YYYY-MM-DD GJM S02
| Test Pile Record | 1157 | 1157 YYYY-MM-DD GJM S02
| Drilled Shaft Concrete Volume Plot | 393 | 0393 YYYY-MM-DD GJM Truss Sta 24+65
| Drilled Shaft Excavation/concrete placement for bridges | 1448 | 1448 YYYY-MM-DD GJM Truss Sta 24+65
| Micropile Installation Record | 1989 | 1989 YYYY-MM-DD GJM B01 Abut A Pile 24
| Cofferdam Installation, Piling Placement, and Tremie Pour Inspector's Checklist | 1990 | 1990 YYYY-MM-DD GJM B01 Abut A
| Permit To Place | 1125 | 1125 YYYY-MM-DD GJM B01 Superstructure
| Sheet Piling and Cofferdams | Calc | Calc YYYY-MM-DD GJM (Name of item of work)
| Precast Concrete Beams | Calc | Calc YYYY-MM-DD GJM (Name of item of work)
| Mechanically Stablized earth retaining wall system checklist | 1447 | 1447 YYYY-MM-DD
| Hydrodemolition Documents | Calc | Calc YYYY-MM-DD GJM (Name of item of work)
| Waterproofing | Calc | Calc YYYY-MM-DD GJM (Name of item of work)
| Waste Profile Forms | Calc | Calc YYYY-MM-DD GJM (Name of item of work)
| Bridge Deck Check List | 2082 | 2082 YYYY-MM-DD GJM B01
| Bridge Deck overlay Check List | 2083 | 2083 YYYY-MM-DD GJM B01
| Bridge Painting Check List | 2081 | 2081 YYYY-MM-DD GJM B01
| Sketches and Calculations | Calc | Calc YYYY-MM-DD GJM (Name of item of work)
208 | Miscellaneous
| Permit To Place | 1125 | 1125 YYYY-MM-DD GJM ADA Ramp SW Johnson Rd
| Fencing |  | (Name of item of work) YYYY-MM-DD GJM
| General Comps. |  | (Name of item of work) YYYY-MM-DD GJM
| Guardrail |  | (Name of item of work) YYYY-MM-DD GJM
| Slope Restoration |  | (Name of item of work) YYYY-MM-DD GJM
| Inspector's Daily Record of Contact Removal Items | 1122A | 1122A YYYY-MM-DD GJM
| Sketches and Calcs | Calc | Calc YYYY-MM-DD GJM (Name of item of work)
| Permanent Traffic Signs |  | (Name of item of work) YYYY-MM-DD GJM
| Electrical Items |  | (Name of item of work) YYYY-MM-DD GJM
208-1 | Traffic
| Inspector's Checklist For Inspection for Solar Boards | 1013S | 1013S YYYY-MM-DD GJM
| Mobility Report | 1998 | 1998 YYYY-MM-DD GJM
| Pavement Marking Material Verification Checklist | 1585 | 1585 YYYY-MM-DD GJM
| Drilled Shaft Inspection Record for Highway signs, Luminaires, TS | 1988 | 1988 YYYY-MM-DD GJM Truss Sta 24+65
| Drilled Shaft Concrete Volume Plot | 393 | 0393 YYYY-MM-DD GJM Truss Sta 24+65
| Traffic Control Report Form | 1996 | 1996 YYYY-MM-DD GJM
| Traffic Advisories | Document | (Name of advisory) YYYY-MM-DD GJM
209 | Delivery Tickets(Miscellaneous)
300 | MATERIAL TESTING
300 | Material Source List
Approved
| Material Source List | 501 | 0501 001 | Permanent
301 | Density
| Independent Assurance Test | 509 | 0509 YYYY-MM-DD GJM | Permanent
| Moisture and Density Determination of Soils | 0582-B | 0582-B YYYY-MM-DD GJM | Permanent
| Record of Density Retests | 0582-A | 0582-A YYYY-MM-DD GJM | Permanent
303 | Bases
| Aggregate Inspection Daily Report | 1900 | 1900 001 | Permanent
| Independent Assurance Test | 504 | 0504 YYYY-MM-DD GJM | Permanent
| Mechanical Analysis Report | 1901 | 1901 001 | Permanent
304 | Drainage
| Field Report For Concrete Pipe | 1920 | 1920 YYYY-MM-DD GJM 36 inch | Permanent
| Field Report For Precast Drainage Items | 1920A | 1920A YYYY-MM-DD GJM 60 inch Structure | Permanent
305 | Hot Mix Asphalt (HMA)
| Daily Report of Bituminous Plant Inspection | 1903 | 1903 YYYY-MM-DD GJM XYZ Supplier Plant 1 | Permanent
| Contractor's Quality Control Tests for PWL | 1903-C | 1903C YYYY-MM-DD PWL 5E1 Lot 1 Sublot 2 | Permanent
| Contractor's Quality Control Tests for STA | 1903-C | 1903C YYYY-MM-DD 5E1 STA 3 | Permanent
| HMA Quality Assurance Plan | 587 | 587 | Permanent
| Independent Assurance Test | 1842 | 1842 | Permanent
| Job Mix Formula (JMF) Bituminous Field Communication | 1911 | 1911 5E3 123145 | Permanent
| Report of Compacted Bituminous Mixture Core Density & Percent for PWL | 1907 | 1907 YYYY-MM-DD PWL 5E1 Lot 1 Sublot 2 | Permanent
| Report of Compacted Bituminous Mixture Core Density & Percent for STA | 1907 | 1907 YYYY-MM-DD 5E1 STA 3 | Permanent
| Report of Compacted Bituminous Mixture Core Density & Percent | 1907J | 1907J YYYY-MM-DD Lot 1 Sublot 2 123145 | Permanent
| Report of Quality Assurance Testing for PWL | 1903-B | 1903B YYYY-MM-DD PWL 5E1 Lot 1 Sublot 2 | Permanent
| Report of Quality Assurance Testing for STA | 1903-B | 1903B YYYY-MM-DD 5E1 STA 3 | Permanent
| Pre-production Meeting Minutes |  | Pre-production Meeting Minutes | Permanent
| PWL spreadsheet |  | (Name of item of work) YYYY-MM-DD GJM | Permanent
| QA/QC Plan |  | HMA QA Plan | Permanent
306 | Concrete
| Concrete Plant Equipment Inspection Report | 580 | 0580 YYYY-MM-DD GJM XYZ Supplier Plant 1 | Permanent
| Concrete Plant Inspection | 0580A | 0580A YYYY-MM-DD GJM XYZ Supplier Plant 1 | Permanent
| Concrete Proportioning Plant Report | 1174 | 1174 YYYY-MM-DD GJM XYZ Supplier Plant 1 | Permanent
| Independent Assurance Test | 503 | 0503 YYYY-MM-DD GJM | Permanent
| JMF Concrete Field Communication | 1976 | 1174 YYYY-MM-DD GJM XYZ Supplier Plant 1 | Permanent
| Pavement Core Record | 502 | 0502 YYYY-MM-DD GJM Sta 24+65 | Permanent
| Weekly Summary Of Cert. Concrete/Comm. Central-Transit Mix | 1155 | 1155 YYYY-MM-DD CC152 | Permanent
| QA/QC Plan |  | Conc QC Plan YYYY-MM-DD | Permanent
| Pre-production Meeting Minutes |  | Pre-production Meeting Minutes | Permanent
| PWL spread sheets |  | (Name of item of work) YYYY-MM-DD GJM | Permanent
306-1 | Concrete Cylinder Break
| Concrete Cylinder Break | 1999 | 1999 YYYY-MM-DD GJM B01 | Permanent
| Report Of Modulus Of Rupture | 1160 | 1160 YYYY-MM-DD GJM Concrete Pavement 24+65 | Permanent
307 | Structure
| Magnetic Particle Inspection Report | 0538-A | 0538A YYYY-MM-DD GJM B04 Beam A Diaphram 1 | Permanent
| Report Of Ultrasonic Examination Of Welds | 0538-B | 0538B YYYY-MM-DD GJM B04 Beam A Diaphram 1 | Permanent
| Structure Foundation Inspection | 579 | 0579 YYYY-MM-DD GJM S02 Pier 2 | Permanent
| Welding Plan | 395 | 0395 123145 | Permanent
| Welding Certs |  | Welder Smith John *1G SMAW | Permanent
308 | Miscellaneous
| Report of Test | Test | Test 001 | Permanent
308-1 | Traffic
| Cantilever and Bridge Mount Inspection | 519 | 0519 YYYY-MM-DD GJM Cantiliever Sta 24+65 Rt | Permanent
309 | Material Certifications
| Shipment Of Tested Stock Report | 1922 | 1922 001 | Permanent
| Material Certifications | Cert | Cert 001 | Permanent
| Test Report | Test | Test 001 | Permanent
400 | INTERNAL USE ONLY
400 | Contractor Performance Evaluations(CPE)
| Contractor Performance Evaluations(CPE) |  | CPE 001 ABC Contracting
401 | Certified Payrolls
| Certified Payrolls | CP-347 | CP347 YYYY-MM-DD ABC Contracting
| Wage and Hour Division (WHD) | WH-347 | WH347 YYYY-MM-DD ABC Contracting
| Unapproved | WH-347
| Certified Payroll Review Checklist | 1952 | 1952 YYYY-MM-DD ABC Contracting
| Certified Payroll Status Log | 1954 | 1954 ABC Contracting
| Contractor’s Certified Payroll | 1955 | 1955 YYYY-MM-DD ABC Contracting
| Jobsite Poster Inspection Checklist | 1967 | 1967 YYYY-MM-DD GJM
| Minimum Wage Rate - Interview Sheet Tier1 | 1156-T1 | 1156-T1 YYYY-MM-DD ABC Contracting
| Minimum Wage Rate - Interview Sheet Tier2 | 1156-T2 | 1156-T2 YYYY-MM-DD ABC Contracting
Apprenticeship & Trainee Reports
402 | Consultant Contracts
403 | Internal Claim Documents
| Contractor Claims |  | Claim 001 Lead Paint Removal ABC Contracting | 7 Years
| Blue Book Sheets |  | Blue Book Cat 650 XLT ABC Contracting | 7 Years
404 | QA Random Numbers
| Concrete |  | Conc Rand Number
| HMA |  | HMA Rand Number
| MDOT Oversight (local agency specific) | 1967 | 1967 YYYY-MM-DD GJM
|  | 1963 | 1963 YYYY-MM-DD GJM
|  | 1964 | 1964 YYYY-MM-DD GJM
|  | 1965 | 1965
|  | 1147 | 1147
|  | 1969 | 1969
|  | 1970 | 1970
|  | 1971 | 1971
|  | 1973 | 1973
|  | 1952 | 1952 YYYY-MM-DD ABC Contracting
Recommended 2nd Descriptors: | Positions: | 1F, 2F, 3F, 4F, 1G, 2G, 3G, 4G, etc.
| Type: | SMAW, SAW, FCAW, GMAW, TIG